## Full1
|  | Year 1 (2014) |  |  |  | Year 2 (2015) |  |  |  | Year 3 (2016) |  |  |  | Year 4 (2017) |  |  |  | Year 5 (2018)
|  | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De
*continues in following pages (1/3) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60
WP1 | Project management
Task 1.1 Establishment of management bodies | bar: Year 1 (2014) Ma 3
Task 1.2 Kick off meeting | bar: Year 1 (2014) Ma 3
Task 1.3 Annual Coordination Meeting | bar: Year 2 (2015) Ma 15; Year 3 (2016) Ma 27; Year 4 (2017) Ma 39; Year 5 (2018) Ma 51; Year 5 (2018) De 60
Task 1.4 Communication with the European Commission (EC) | bar: Year 2 (2015) Ma 15; Year 3 (2016) Ma 27; Year 4 (2017) Ma 39; Year 5 (2018) Ma 51; Year 5 (2018) De 60
Task 1.5 Mid-term evaluation of progress | bar: Year 2 (2015) Ma 15; Year 3 (2016) Ma 27; Year 4 (2017) Ma 39; Year 5 (2018) Ma 51; Year 5 (2018) De 60
Task 1.6 Interactions with other projects
GWP | Reproduction & genetics-meagre
WP2 | Reproduction & genetics-meagre
Task 2.1 Evaluation of the genetic variation in captive meagre broodstocks | bar: Year 1 (2014) Ma 3 to Year 1 (2014) De 12
Task 2.2 Development of protocols for paired crossing in spontaneous spawning | bar: Year 1 (2014) Ma 3 to Year 2 (2015) Se 21
Task 2.3 Description of sperm characteristics and cryopreservation methods | bar: Year 1 (2014) De 12 to Year 3 (2016) De 36
Task 2.4 Development of in vitro fertilization methods for planned crosses | bar: Year 1 (2014) De 12 to Year 3 (2016) De 36
Task 2.5 Development of Single Nucleotide Polymorphisms (SNP) marker tools for the genetic characterization of fast and slow growers | bar: Year 1 (2014) Ma 3 to Year 3 (2016) Ju 30
WP3 | Reproduction & genetics-greater amberjack
Task 3.1 Description of the reproductive cycle of greater amberjack | bar: Year 1 (2014) Ma 3 to Year 4 (2017) De 48
Task 3.2 Development of an optimized spawning induction protocol for captive greater amberjack in the Mediterranean
Task 3.3 Development of an optimized spawning induction protocol for captive greater amberjack in the eastern Atlantic
Task 3.4 Development of an optimized spawning induction protocols for F1 greater amberjack in the eastern Atlantic | bar: Year 1 (2014) Ma 3 to Year 4 (2017) De 48
Task 3.5 Spawning induction of greater amberjack and egg collection in cages | bar: Year 2 (2015) Ma 15 to Year 5 (2018) Ju 54
WP4 | Reproduction & genetics-pike perch
Task 4.1 Evaluation of the genetic variation in available domesticated broodstocks of pike perch | bar: Year 1 (2014) Ma 3 to Year 1 (2014) De 12
Task 4.2 Evaluation of the genetic variation in non-domesticated broodstocks of pike perch | bar: Year 1 (2014) Ma 3 to Year 2 (2015) Ju 18
WP5 | Reproduction & genetics-Atlantic halibut
Task 5.1 Documentation of reproductive performance in wild-captured vs cultured female Atlantic halibut | bar: Year 1 (2014) Ma 3 to Year 3 (2016) Ju 30
Task 5.2 GnRH implant therapy as a means to improve spawning performance | bar: Year 1 (2014) Ma 3 to Year 3 (2016) Ju 30
Task 5.3 Fecundity regulation | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
WP6 | Reproduction & genetics-wreckfish
Task 6.1 Collect wild fish to establish new broodstocks | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 6.2 Describe reproductive cycle | bar: Year 1 (2014) Ma 3 to Year 4 (2017) De 48
Task 6.3 Development of spawning induction procedures
Task 6.4 Evaluation of sperm characteristics and cryopreservation protocols | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
WP7 | Reproduction & genetics-grey mullet
Task 7.1 Evaluation of the effectiveness of hormone-based treatments on synchronizing gonadal development | bar: Year 1 (2014) Ma 3 to Year 2 (2015) Se 21
Task 7.2 Development of hormone-based treatments for inducing spawning | bar: Year 1 (2014) Ma 3 to Year 3 (2016) Se 33
Task 7.3 Optimization and scale-up of a breeding protocol for grey mullet in captivity | bar: Year 2 (2015) De 24 to Year 5 (2018) De 60
Task 7.4 Assessment of the effects of captivity on first sexual maturity of wild-caught and hatchery-produced fish
Task 7.5 Establish a shipping protocol fro grey mullet eggs | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
GWP | Nutrition
WP8 | Nutrition-meagre
Task 8.1 Improvement of larval weaning feeds | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
Task 8.2 Determination of nutritional requirements to promote feed utilization, consistent growth rates and fish welfare | bar: Year 1 (2014) De 12 to Year 4 (2017) De 48
WP9 | Nutrition-greater amberjack
Task 9.1 Improve larval enrichement products to enhance production of larvae and juveniles | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 9.2 Development of diets for grow-out of amberjack to maximize growth | bar: Year 2 (2015) Ju 18 to Year 5 (2018) Se 57
Task 9.3 Design adequate feeding regimes for broodstock to optimize reproduction
WP10 | Nutrition-pike perch
Task 10.1 Effect of selected dietary nutrients on pikeperch larval development and performance | bar: Year 1 (2014) Ju 6 to Year 4 (2017) Ju 42
Task 10.2 Effects of pikeperch early fatty acid nutrition on long-term stress sensitivity | bar: Year 1 (2014) De 12 to Year 4 (2017) De 48
|  | Year 1 (2014) |  |  |  | Year 2 (2015) |  |  |  | Year 3 (2016) |  |  |  | Year 4 (2017) |  |  |  | Year 5 (2018)
|  | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De
*continues from previous page (2/3) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60
WP11 | Nutrition-Atlantic halibut
Task 11.1 Early weaning of Atlantic halibut | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 11.2 Development of a production strategy for ongrown Artemia | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
Task 11.3 Nutrient retention and digestive physiology of Atlantic halibut juveniles fed Artemia nauplii or on-grown Artemia | bar: Year 2 (2015) Ma 15 to Year 3 (2016) De 36
Task 11.4 Comparison of nutrient retention in Atlantic halibut larvae reared in RAS vs FTS | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 11.5 Effect of dietary PL on digestion, absorption and metabolism of lipids in Atlantic halibut juveniles | bar: Year 3 (2016) Ma 27 to Year 4 (2017) De 48
WP12 | Nutrition-wreckfish
Task 12.1 Live preys and enrichments for wreckfish larvae | bar: Year 2 (2015) Ma 15 to Year 2 (2015) Ju 18; Year 3 (2016) Ma 27 to Year 3 (2016) Ju 30; Year 4 (2017) Ma 39 to Year 4 (2017) Ju 42; Year 5 (2018) Ma 51 to Year 5 (2018) Ju 54
Task 12.2 Influence of broodstock feeds for fecundity and spawn quality | bar: Year 1 (2014) De 12 to Year 5 (2018) Se 57
WP13 | Nutrition-grey mullet
Task 13.1 Improvement of larval performance through adequate first feeding regimes | bar: Year 1 (2014) Ma 3 to Year 3 (2016) Ju 30
Task 13.2 Determining grey mullet nutritional needs for improved weaning to a dry diet | bar: Year 2 (2015) Se 21 to Year 3 (2016) De 36
Task 13.3 Determining grey mullet nutritional needs for a more cost-effective production | bar: Year 3 (2016) Ma 27 to Year 4 (2017) De 48
Task 13.4 Design adequate feeding regimes for brood stock to optimize reproduction success | bar: Year 4 (2017) Ma 39 to Year 5 (2018) Se 57
GWP | Larval husbandry
WP14 | Larval husbandry-meagre
Task 14.1 Determining the earliest and most cost effective weaning period | bar: Year 1 (2014) Ma 3 to Year 1 (2014) Ju 6; Year 2 (2015) Ma 15 to Year 2 (2015) Ju 18
WP15 | Larval husbandry-greater amberjack
Task 15.1 Effect of feeding regime and probiotics | bar: Year 1 (2014) Ju 6 to Year 3 (2016) Ma 27
Task 15.2 Comparison of semi-intensive and intensive rearing | bar: Year 1 (2014) Ju 6 to Year 3 (2016) Ma 27
Task 15.3 Effect of environmental parameters during rearing | bar: Year 1 (2014) Ju 6 to Year 1 (2014) De 12; Year 2 (2015) Ju 18 to Year 2 (2015) De 24
Task 15.4 Development of industrial protocol | bar: Year 2 (2015) Ju 18 to Year 2 (2015) De 24; Year 3 (2016) Ju 30 to Year 3 (2016) De 36; Year 4 (2017) Ju 42 to Year 4 (2017) De 48
WP16 | Larval husbandry-pike perch
Task 16.1 Optimal combinations of factors to improve larval rearing | bar: Year 1 (2014) Ju 6 to Year 1 (2014) Se 9; Year 2 (2015) Ju 18 to Year 2 (2015) Se 21; Year 3 (2016) Ju 30 to Year 3 (2016) Se 33; Year 4 (2017) Ju 42 to Year 4 (2017) Se 45; Year 5 (2018) Ju 54 to Year 5 (2018) Se 57
Task 16.2 Development of an industrial protocol | bar: Year 1 (2014) Ju 6 to Year 1 (2014) Se 9; Year 2 (2015) Ju 18 to Year 2 (2015) Se 21; Year 3 (2016) Ju 30 to Year 3 (2016) Se 33; Year 4 (2017) Ju 42 to Year 4 (2017) Se 45; Year 5 (2018) Ju 54 to Year 5 (2018) Se 57
WP17 | Larval husbandry-Atlantic halibut
Task 17.1 Recirculation (RAS) vs Flow through (FT) systems during yolk sac and first feeding stages and the effects on larval survival, quality and growth | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 17.2 The effect of probiotics on larval microbiota and survival | bar: Year 1 (2014) De 12 to Year 4 (2017) Ju 42
Task 17.3 Production of on-grown Artemia | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
Task 17.4 Comparison of feeding on-grown Artemia versus Artemia nauplii on larval performance | bar: Year 2 (2015) Ma 15 to Year 3 (2016) De 36
WP18 | Larval husbandry-wreckfish
Task 18.1 Development of feeding methodology | bar: Year 1 (2014) Ma 3 to Year 1 (2014) Se 9; Year 2 (2015) Ma 15 to Year 2 (2015) Se 21; Year 3 (2016) Ma 27 to Year 3 (2016) Se 33; Year 4 (2017) Ma 39 to Year 4 (2017) De 48
Task 18.2 Defining optimum conditions for larval rearing | bar: Year 1 (2014) Ma 3 to Year 1 (2014) Se 9; Year 2 (2015) Ma 15 to Year 2 (2015) Se 21; Year 3 (2016) Ma 27 to Year 3 (2016) Se 33; Year 4 (2017) Ma 39 to Year 4 (2017) De 48
WP19 | Larval husbandry-grey mullet
Task 19.1 Effect of algal type and concentration on larval performance | bar: Year 1 (2014) Ma 3 to Year 4 (2017) De 48
Task 19.2 Comparing the selected microalgae type and protocol with lyophilized substitute | bar: Year 2 (2015) De 24 to Year 4 (2017) De 48
Task 19.3 Determine the effect of co-feeding ciliates and rotifers on digestive tract maturation and enzyme production | bar: Year 1 (2014) Ma 3 to Year 3 (2016) De 36
Task 19.4 Determine when to wean larvae and to feed weaning diet type according to DT maturation and the shift from carnivorous to omnivorous feeding | bar: Year 2 (2015) Ma 15 to Year 3 (2016) De 36
Task 19.5 Testing the improved grey mullet larval rearing protocol in a commercial hatchery | bar: Year 3 (2016) Se 33 to Year 5 (2018) Ju 54
GWP | Grow out husbandry
WP20 | Grow out husbandry-meagre
Task 20.1 Size variability at juveniles | bar: Year 1 (2014) Ju 6 to Year 1 (2014) Se 9; Year 2 (2015) Ju 18 to Year 2 (2015) De 24
Task 20.2 Effect of rearing environment | bar: Year 1 (2014) Se 9 to Year 4 (2017) Ma 39
Task 20.3 Development of feeding methodology | bar: Year 1 (2014) Ju 6 to Year 4 (2017) Ju 42
WP21 | Grow out husbandry-greater amberjack
Task 21.1 Development of rearing method in cages | bar: Year 1 (2014) De 12 to Year 5 (2018) Se 57
Task 21.2 Development of feeding methods | bar: Year 1 (2014) Se 9 to Year 4 (2017) Ju 42
Task 21.3 Development of appropriate husbandry practise | bar: Year 2 (2015) Ju 18 to Year 5 (2018) Se 57
WP22 | Grow out husbandry-pike perch
Task 22.1 Effect of husbandry practices and environmental factors on pikeperch growth, immune and physiological status | bar: Year 1 (2014) Se 9 to Year 2 (2015) De 24
Task 22.2 Characterization of pikeperch growth, immune and physiological status in farm conditions | bar: Year 2 (2015) Se 21 to Year 4 (2017) Ju 42
Task 22.3 Effect of pikeperch domestication level and geographical origin on growth and stress sensitivity | bar: Year 3 (2016) Ma 27 to Year 4 (2017) De 48
WP23 | Grow out husbandry-grey mullet
Task 23.1 Determinve the cost-benefit of different weaning diets on the performance and health status of wild juvenile grey mullet | bar: Year 1 (2014) Se 9 to Year 2 (2015) Ju 18
Task 23.2 Compare the effect of feeding an improved grey mullet diet on the grow-out in monoculture of F1 juveniles stocked at two different densities in cement and earthen ponds | bar: Year 1 (2014) Se 9 to Year 3 (2016) Ju 30
Task 23.3 Compare the effect of feeding an improved grey mullet diet on the grow-out in monoculture of wild caught juveniles stocked at two different densities in cement ponds in Greece | bar: Year 1 (2014) De 12 to Year 3 (2016) Ju 30
Task 23.4 Compare the effect of feeding an improved grey mullet diet on the grow-out in monoculture of wild caught juveniles stocked at two different densities in cement ponds in Spain | bar: Year 1 (2014) De 12 to Year 4 (2017) Ju 42
|  | Year 1 (2014) |  |  |  | Year 2 (2015) |  |  |  | Year 3 (2016) |  |  |  | Year 4 (2017) |  |  |  | Year 5 (2018)
|  | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De | Ma | Ju | Se | De
*continues from previous page (3/3) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60
GWP | Fish Health
WP24 | Fish health-meagre
Task 24.1 Systematic Granulomatosis | bar: Year 1 (2014) Ju 6 to Year 5 (2018) Ju 54
Task 24.2 Chronic Ulcerative Dermatopathy | bar: Year 3 (2016) Ma 27 to Year 3 (2016) Se 33; Year 4 (2017) Ma 39 to Year 4 (2017) Se 45
Task 24.3 Anti-parasitic treatments | bar: Year 1 (2014) De 12; Year 2 (2015) De 24; Year 3 (2016) Se 33 to Year 3 (2016) De 36; Year 4 (2017) Se 45
Task 24.4 Nocardia infection in meagre | bar: Year 1 (2014) Ju 6 to Year 5 (2018) Ju 54
Task 24.5 First characterisation of the immune system | bar: Year 1 (2014) Ju 6 to Year 4 (2017) Ju 42
Task 24.6 Monitor specific immune responses | bar: Year 2 (2015) Ju 18 to Year 5 (2018) Ma 51
Task 24.7 Description, diagnosis and treatment of other bacterial/viral infectious diseases occurring in meagre
Task 24.8 Diagnostic-recommendation manual for meager health | bar: Year 5 (2018) Ma 51 to Year 5 (2018) Se 57
WP25 | Fish-health-greater amberjack
Task 25.1 Study of Epitheliocystis during larval rearing | bar: Year 1 (2014) Ju 6; Year 2 (2015) Ju 18; Year 3 (2016) Ju 30; Year 4 (2017) Ju 42 to Year 4 (2017) Se 45
Task 25.2 Promoting resistance to parasitic incidence on greater amberjack | bar: Year 3 (2016) Ju 30 to Year 5 (2018) Se 57
Task 25.3 Identification of immune markers | bar: Year 1 (2014) Ju 6 to Year 4 (2017) Ma 39
Task 25.4 Effectiveness of stocking density and anti-oncomiracidia attaching substances in the control of monogenean parasites | bar: Year 2 (2015) Ma 15 to Year 5 (2018) Se 57
Task 25.5 Description, diagnosis and treatment of other bacterial/viral infectious diseases occurring in greater amberjack
Task 25.6 Diagnostic-recommendation manual for greater amberjack health | bar: Year 5 (2018) Ma 51 to Year 5 (2018) Se 57
WP26 | Fish-health-Atlantic halibut
Task 26.1 Production of VNN capsid protein | bar: Year 1 (2014) Ju 6 to Year 3 (2016) De 36
Task 26.2 Monitor and assess immune response and protection | bar: Year 2 (2015) Ma 15 to Year 4 (2017) Ju 42
GWP | Socioeconomics
WP27 | Socioeconomics-Institutional and organizational context
Task 27.1 External environmental analysis | bar: Year 1 (2014) Ma 3
Task 27.2 Competitive analysis | bar: Year 1 (2014) Ju 6 to Year 1 (2014) De 12
Task 27.3 Opportunities and barriers for growth | bar: Year 1 (2014) De 12
WP28 | Socioeconomics-New product development
Task 28.1 Product concept development: technical and consumer-driven | bar: Year 2 (2015) Ma 15 to Year 2 (2015) Ju 18
Task 28.2 New Product Development | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
Task 28.3 Monitoring technical quality of the products | bar: Year 3 (2016) Ma 27 to Year 5 (2018) Se 57
WP29 | Socioeconomics-Consumer value perceptions and behavioural change
Task 29.1 Consumer value perceptions and segmentation | bar: Year 1 (2014) Ma 3 to Year 2 (2015) De 24
Task 29.2 Consumer sensory perceptions | bar: Year 3 (2016) Ma 27 to Year 3 (2016) Ju 30
Task 29.3 Optimization of intrinsic-extrinsic attribute combinations | bar: Year 3 (2016) Ju 30 to Year 3 (2016) De 36
Task 29.4 Communication effectiveness in behavioural change | bar: Year 4 (2017) Ma 39 to Year 4 (2017) Se 45
WP30 | Socioeconomics-Bussiness model and marketing strategy development
Task 30.1 Business models | bar: Year 4 (2017) Ma 39 to Year 4 (2017) De 48
Task 30.2 New product marketing strategy development | bar: Year 5 (2018) Ma 51 to Year 5 (2018) Ju 54
Task 30.3 Recommendations of industry development and international market expansion | bar: Year 5 (2018) Se 57 to Year 5 (2018) De 60
WP31 | Dissemination
Task 31.1 Project website and brochure
Task 31.2 Annual coordination meetings | bar: Year 2 (2015) Ma 15; Year 3 (2016) Ma 27; Year 4 (2017) Ma 39; Year 5 (2018) Ma 51; Year 5 (2018) De 60
Task 31.3 Presenation of DIVERSIFY at the AQUA EUROPE meetings | bar: Year 1 (2014) Se 9; Year 2 (2015) Se 21; Year 3 (2016) Se 33; Year 4 (2017) Se 45; Year 5 (2018) Se 57
Task 31.4 Scientific presentations and submission of manuscripts | bar: Year 2 (2015) Se 21 to Year 5 (2018) De 60
Task 31.5 Full-day seminar on "Know-how Transfer" of the aquaculture for each of the studies species | bar: Year 5 (2018) Ju 54 to Year 5 (2018) Se 57
Task 31.6 Promotional workshops | bar: Year 3 (2016) De 36; Year 4 (2017) Se 45; Year 5 (2018) Ma 51; Year 5 (2018) Se 57 to Year 5 (2018) De 60
Task 31.7 Dissemination to the food industry and consumers | bar: Year 3 (2016) Ma 27 to Year 5 (2018) De 60