## Group WP list
DIVERSIFY
KBBE 2013.1.2.09. Diversification of fish species and products in aquaculture
Table 1.3 a: | Work package list
Work package | Work package title | Type of activity[2] | Lead | Lead participant short name | Person-months[4] | Start | End
No[1] |  |  | participant |  |  | month[5] | month
No[3]
1 | Project Management | MGT | 1 | HCMR | 81.41 | 1 | 60 | WP1 Management | 5.1018 | 81.41
2 | Reproduction and Genetics | RTD | 3 | IRTA | 321.51 | 1 | 58 | WP2 Reproduction and genetics | 20.1483 | 321.51
3 | Nutrition | RTD | 2 | FCPCT | 197.75 | 1 | 57 | WP3 Nutrition | 12.3925 | 197.75
4 | Larval Husbandry | RTD | 4 | NCM | 167.71 | 1 | 57 | WP4 Larval husbandry | 10.51 | 167.71
5 | Grow out Husbandry | RTD | 1 | HCMR | 307.7 | 6 | 54 | WP5 Grow out husbandry | 19.2828 | 307.7
6 | Fish Health | RTD | 5 | UNIABDN | 247.66 | 5 | 57 | WP6 Fish health | 15.5203 | 247.66
7 | Socioeconomics | RTD | 6 | LEI | 231.77 | 1 | 60 | WP7 Socioeconomics | 14.5245 | 231.77
8 | Dissemination | OTHER | 18 | CTAQUA | 40.21 | 1 | 60 | WP8 Dissemination | 2.5199 | 40.21
|  | TOTAL |  |  | 1595.72 |  |  |  |  | 1595.72
[1] Work package number: WP 1 – WP n.
[2] Please indicate one activity per work package: RTD = Research and technological development (; DEM = Demonstration; MGT = Management of the consortium; OTHER = Other specific activities, if applicable in this call including any activities to prepare for the dissemination and/or exploitation of project results, and coordination activities) According to the description of the funding scheme given previously.
[3] Number of the participant leading the work in this work package.
[4] The total number of person-months allocated to each work package.
[5] Measured in months from the project start date (month 1).

## WP list
Work package | Work package title | Type of activity[2] | Lead | Lead participant short name |  | Person-months[4] | Start | End
No[1] |  |  | participant |  | Lea participant scientist |  | month[5] | month
No[3]
1 | Project Management | MGT | 1 | HCMR | CC Mylonas | 81.41 | 1 | 60
Group WPs | Reproduction and Genetics | RTD | 3 | IRTA | N Duncan | 321.51 | 1 | 60
2 | Reproduction & genetics-meagre | RTD | 3 | IRTA | N Duncan | 40.65 | 1 | 36
3 | Reproduction & genetics-amberjack | RTD | 13 | UNIBA | A Corriero | 195.4 | 1 | 54
4 | Reproduction & genetics-pikeperch | RTD | 1 | HCMR | C Tsigenopoulos | 5 | 1 | 16
5 | Reproduction & genetics-Atlantic halibut | RTD | 7 | IMR | B Norberg | 20.5 | 1 | 36
6 | Reproduction & genetics-wreckfish | RTD | 8 | IEO | T Peleteiro | 34.16 | 1 | 54
7 | Reproduction & genetics-grey mullet | RTD | 4 | IOLR | H Rosenfeld | 25.8 | 1 | 60
Group WPs | Nutrition | RTD | 2 | FCPCT | D Montero | 197.75 | 1 | 57
8 | Nutrition-meagre | RTD | 2 | FCPCT | L Robaina | 27 | 1 | 48
9 | Nutrition-greater amberjack | RTD | 2 | FCPCT | M Izquierdo | 46.8 | 1 | 58
10 | Nutrition-pikeperch | RTD | 21 | DTU | I Lund | 35 | 4 | 48
11 | Nutrition-Atlantic halibut | RTD | 17 | NIFES | K Hamre | 14.2 | 1 | 48
12 | Nutrition-wreckfish | RTD | 8 | CMRM | F Linares | 6.6 | 1 | 57
13 | Nutrition-grey mullet | RTD | 4 | IOLR | W Koven | 68.15 | 1 | 55
Group WPs | Larval Husbandry | RTD | 4 | IOLR | W Koven | 167.71 | 1 | 57
14 | Larval husbandry-meagre | RTD | 3 | IRTA | A Estevez | 3.7 | 1 | 18
15 | Larval husbandry-greater amberjack | RTD | 2 | FCPCT | C Mari Hernandez | 79.5 | 5 | 48
16 | Larval husbandry-pikeperch | RTD | 9 | UL | P Fontaine | 34.7 | 1 | 57
17 | Larval husbandry-Atlantic halibut | RTD | 7 | IMR | B Norberg | 20 | 1 | 48
18 | Larval husbandry-wreckfish | RTD | 8 | IEO | T Peleteiro | 14.81 | 1 | 48
19 | Larval husbandry-grey mullet | RTD | 4 | IOLR | W Koven | 15 | 1 | 55
Group WPs | Grow out Husbandry | RTD | 1 | HCMR | N Papandroulakis | 307.7 | 6 | 57
20 | Grow out husbandry-meagre | RTD | 3 | IRTA | N Duncan | 91.5 | 6 | 42
21 | Grow out husbandry-greater amberjack | RTD | 1 | HCMR | N Papandroulakis | 111.4 | 8 | 57
22 | Grow out husbandry-pikeperch | RTD | 16 | FUNDP | P Kestemont | 61 | 8 | 48
23 | Grow out husbandry-mullet | RTD | 4 | IOLR | W Koven | 43.8 | 9 | 40
Group WPs | Fish Health | RTD | 5 | UNIABDN | C Secombes | 247.66 | 5 | 57
24 | Fish health-meagre | RTD | 5 | HCMR | P Katharios | 148.4 | 5 | 54
25 | Fish health-greater amberjack | RTD | 5 | UNIABD | C Secombes | 95.1 | 6 | 57
26 | Fish health-Atlantic halibut | RTD | 7 | IMR | P Sonal | 4.16 | 4 | 40
Group WPs | Socioeconomics | RTD | 6 | DLO | G Tacken | 231.77 | 1 | 60
27 | Socioeconomics-institutional and organizational context | RTD | 6 | DLO | G Tacken | 23.65 | 1 | 12
28 | Socioeconomics-new product development | RTD | 3 | IRTA | Lluis Guerrero | 77.85 | 13 | 58
29 | Socioeconomics-consumer value perceptions and behavioural change | RTD | 11 | AU | A Krystallis | 75.48 | 1 | 44
30 | Socioeconomics-business model and marketing strategy development | RTD | 10 | TU/e | E Nijssen | 54.79 | 43 | 60
31 | Dissemination | OTHER | 18 | CTAQUA | R Robles | 40.21 | 1 | 60
|  | TOTAL |  |  |  | 1595.72

## WT6 Project effort beneficiary
DIVERSIFY
KBBE 2013.1.2.09. Diversification of fish species and products in aquaculture
| Table 1.3 e: | Summary of staff effort
| Participant no./short name | WP1 Mgmt | WP2 Repro | WP3 Nutrition | WP4 Larvae | WP5 Grow out | WP6 Health | WP7 SocioEco | WP8 Dissemination | Total person months
RTDs | 1. HCMR | 55 | 49.9 | 6 | 17 | 63 | 90.1 | 42 | 8 | 331
| 2. FCPCT | 5 | 26 | 65 | 40 | 36 | 84 | 0 | 0 | 256
| 3. IRTA | 1.35 | 19.9 | 1.1 | 6.4 | 15 | 23 | 29.25 | 1 | 97
| 4.IOLR | 2 | 21 | 38 | 9 | 2 | 0 | 0 | 0 | 72
| 5. UNIABDN | 1 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 38
| 6. LEI | 2 | 0 | 0 | 0 | 0 | 0 | 35.18 | 0 | 37.18
| 7. IMR | 0.5 | 8 | 2 | 13 | 0 | 4.16 | 0 | 1 | 28.66
| 8. IEO | 0.5 | 12.2 | 3.9 | 9.7 | 3.4 | 1.1 | 0 | 0.7 | 31.5
| 9. UL | 1 | 1 | 0 | 13 | 18 | 0 | 0 | 1 | 34
| 10. TU/e | 0.5 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 27.5
| 11. AU | 0.5 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 34.5
| 12. APROMAR | 0.61 | 0 | 0 | 0 | 0 | 0 | 17.14 | 2.74 | 20.49
| 13. UNIBA | 0.5 | 33.7 | 5.3 | 0 | 0 | 0 | 0 | 1.5 | 41
| 14. IFREMER | 0.25 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 9
| 15. ULL | 0.5 | 8.1 | 18.5 | 9.8 | 4.5 | 5 | 6.5 | 0 | 52.9
| 16. FUNDP | 0.5 | 0 | 8 | 0 | 26 | 0 | 0 | 0 | 34.5
| 17. NIFES | 0.5 | 1 | 6 | 1 | 0 | 0 | 0 | 0 | 8.5
| 18. CTAQUA | 0.5 | 0 | 3.75 | 0 | 5.8 | 0 | 16.5 | 13.1 | 39.65
| 19. CMRM | 0.5 | 11.7 | 3.5 | 3.1 | 0 | 0 | 0 | 0 | 18.8
| 20. SARC | 0.5 | 0 | 5.7 | 0 | 0 | 3.3 | 0 | 0 | 9.5
| 21. DTU | 0.5 | 0 | 7.5 | 4.5 | 7 | 0 | 0 | 0 | 19.5
| 22. SWH | 0.5 | 11 | 0 | 6 | 0 | 0 | 0 | 0 | 17.5
SMEs | 23. ARGO | 0.5 | 80 | 0 | 0 | 30 | 0 | 0.1 | 0 | 110.6
| 24. ITICAL | 0.29 | 12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 12.49
| 25. DOR | 0.5 | 4 | 0 | 4 | 10 | 0 | 0.1 | 0 | 18.6
| 26. GEI | 0.5 | 1.5 | 0 | 0 | 12 | 0 | 0 | 0 | 14
| 27. FORKYS | 0.5 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 30.5
| 28. CANEXMAR | 0.5 | 0 | 12 | 0 | 45 | 0 | 0.1 | 0 | 57.6
| 29. ASIALOR | 0.25 | 0 | 4.5 | 7.5 | 5 | 0 | 0 | 0 | 17.25
| 30. CULMAREX | 0.1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1.1
| 31. IRIDA | 0.25 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4.25
New | 32. MC2 | 0.25 | 2.06 | 0 | 1.01 | 0 | 0 | 0 | 0 | 3.32
| 33. FGM | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.75
| 34. BFVi | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42 | 0.58
| 35. MASZ | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.25
| 36. ANF | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 3
| 37. EUFIC | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.25
| 38. HRH | 0.6 | 0 | 0 | 0 | 0 | 0 | 23.8 | 0 | 24.4
| 39. F2B | 0.3 | 0 | 7 | 7.7 | 5 | 0 | 0.1 | 0 | 20.1
| 40. GMF | 0.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| Total | 81.41 | 321.51 | 197.75 | 167.71 | 307.7 | 247.66 | 231.77 | 40.21 | 1595.72

## WT7 Project effort by activity
DIVERSIFY | Ammend 3 (Ittical/ASIALOR) |  | 2016-10-11 |  |  |  | Indicates modification in Amend 3
KBBE 2013.1.2.09. Diversification of fish species and products in aquaculture |  |  |  | Amnd 3 |  |  |  |  | Amnd 3 |  |  |  |  | Amnd 3 | [6 empty] | Amnd 3 | Amnd 3 |  |  |  | Amnd 3 | Amnd 3 |  | Amnd 3 |  |  | Amnd 3 | Amnd 2 | [7 empty] | Amnd 3 | Amnd 3 | Amnd 3
Calculation of staff effort per parter and sub WP
[8 empty] | RTD partners | [6 empty] | RTD partners |  |  |  |  | RTD partners | [5 empty] | SME partners | [8 empty] | New Partners | [6 empty] | Amendment 3
Work Package (Proposal) | Title | DOW WP | Total | 1. HCMR | 2. FCPCT | 3. IRTA | 4. IOLR | 5. UNIABDN | 6.DLO | 7. IMR | 8. IEO | 9. UL | 10. TU/e | 11. AU | 12. APROMAR | 13. UNIBA | 14. IFREMER | 15. ULL | 16. FUNDP | 17. NIFES | 18. CTAQUA | 19. CMRM | 20. SARC | 21. DTU | 22. SWH | 23. ARGO | 24. ITICAL | 25. DOR | 26. GEI | 27. FORKYS | 28. CANEXMAR | 29. ASIALOR | 30. CULMAREX | 31. IRIDA | 32. MC2 | 33. FGM | 34. BVFi | 35. MASZ | 36. ANF | 37. EUFIC | 38. HRH | 39. F2B | 40. GMF
|  |  | 1595.72 | 331 | 256 | 97 | 72 | 38 | 37.18 | 28.66 | 31.5 | 34 | 27.5 | 34.5 | 20.49 | 41 | 9 | 52.9 | 34.5 | 8.5 | 39.65 | 18.8 | 9.5 | 19.5 | 17.5 | 110.6 | 12.49 | 18.6 | 14 | 30.5 | 57.6 | 17.25 | 1.1 | 4.25 | 3.32 | 2.75 | 0.58 | 3.25 | 3 | 3.25 | 24.4 | 20.1 | 10
WP1 Management | Management | 1 | 81.41 | 55 | 5 | 1.35 | 2 | 1 | 2 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.61 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.29 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.1 | 0.25 | 0.25 | 0.25 | 0.16 | 0.25 | 0.75 | 0.25 | 0.6 | 0.3 | 0.5
WP2 Reproduction and Genetics |  |  | 321.51 | 49.9 | 26 | 19.9 | 21 | 0 | 0 | 8 | 12.2 | 1 | 0 | 0 | 0 | 33.7 | 8.75 | 8.1 | 0 | 1 | 0 | 11.7 | 0 | 0 | 11 | 80 | 12.2 | 4 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
2.1 | Reproduction - meagre | 2 | 40.65 | 15 | 7 | 15.9 | [10 empty] | 2.75
2.2 | Reproduction - amberjack | 3 | 195.4 | 22 | 19 |  | 14 |  |  |  | 5.6 |  |  |  |  | 30 | 2.5 | 3.8 | [7 empty] | 80 | 9 | [15 empty] | 9.5
2.3 | Reproduction - pikeperch | 4 | 5 | 4 | [7 empty] | 1
2.4 | Reproduction - halibut | 5 | 20.5 | 0.5 | [5 empty] | 8 | [9 empty] | 1 |  |  |  |  | 11
2.5 | Reproduction - wreckfish | 6 | 34.16 | 7.9 |  | 2 |  |  |  |  | 6.6 | [5 empty] | 3 | 0.9 |  |  |  | 11.7 | [12 empty] | 2.06
2.6 | Reproduction - mullet | 7 | 25.8 | 0.5 |  | 2 | 7 | [8 empty] | 3.7 | 0.5 | 3.4 | [8 empty] | 3.2 | 4 | 1.5
WP3 Nutrition |  |  | 197.75 | 6 | 65 | 1.1 | 38 | 0 | 0 | 2 | 3.9 | 0 | 0 | 0 | 0 | 5.3 | 0 | 18.5 | 8 | 6 | 3.75 | 3.5 | 5.7 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0
3.1 | Nutrition - meagre | 8 | 27 | 0 | 20 | 0 | [11 empty] | 4.5 |  | 0 |  |  | 1.5 | 1
3.2 | Nutrition - amberjack | 9 | 46.8 | 6 | 18 | [5 empty] | 2.8 | [6 empty] | 5.5 |  |  |  |  | 2.5 | [7 empty] | 12
3.3 | Nutrition - pikeperch | 10 | 35 |  | 5 |  | 0 | [10 empty] | 4 | 8 |  |  |  |  | 6.5 | [7 empty] | 4.5 | [9 empty] | 7
3.4 | Nutrition - halibut | 11 | 14.2 | [6 empty] | 2 | [7 empty] | 4.5 |  | 6 |  |  | 1.7
3.5 | Nutrition - wreckfish | 12 | 6.6 |  | 2 | [5 empty] | 1.1 | [10 empty] | 3.5 | 0
3.6 | Nutrition - mullet | 13 | 68.15 |  | 20 | 1.1 | 38 | [8 empty] | 5.3 |  |  |  |  | 3.75
WP4 larval husbandry |  |  | 167.71 | 17 | 40 | 6.4 | 9 | 0 | 0 | 13 | 9.7 | 13 | 0 | 0 | 0 | 0 | 0 | 9.8 | 0 | 1 | 0 | 3.1 | 0 | 4.5 | 6 | 0 | 0 | 4 | 0 | 15 | 0 | 7.5 | 0 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7 | 0
4.1 | Larval husbandry - meagre | 14 | 3.7 |  |  | 2.4 | [11 empty] | 1.3
4.2 | Larval husbandry - amberjack | 15 | 79.5 | 10.5 | 40 | [5 empty] | 5.5 | [6 empty] | 8.5 | [11 empty] | 15
4.3 | Larval husbandry - pikeperch | 16 | 34.7 |  |  | 2 | [5 empty] | 13 | [11 empty] | 4.5 | [7 empty] | 7.5 | [9 empty] | 7.7
4.4 | Larval husbandry - halibut | 17 | 20 | [6 empty] | 13 | [9 empty] | 1 |  |  |  |  | 6
4.5 | Larval husbandry - wreckfish | 18 | 14.81 | 6.5 | [6 empty] | 4.2 | [10 empty] | 3.1 | [12 empty] | 1.01
4.6 | Larval husbandry - mullet | 19 | 15 |  |  | 2 | 9 | [20 empty] | 4
WP5 Grow out husbandry |  |  | 307.7 | 63 | 36 | 15 | 2 | 0 | 0 | 0 | 3.4 | 18 | 0 | 0 | 0 | 0 | 0 | 4.5 | 26 | 0 | 5.8 | 0 | 0 | 7 | 0 | 30 | 0 | 10 | 12 | 15 | 45 | 5 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
5.1 | Grow out husbandry - meagre | 20 | 91.5 | 48.5 |  | 12 | [19 empty] | 30 | [6 empty] | 1
5.2 | Grow out husbandry - amberjack | 21 | 111.4 | 7.5 | 36 | [5 empty] | 3.4 | [6 empty] | 4.5 | [11 empty] | 15 | 45
5.3 | Grow out husbandry - pike perch | 22 | 61 |  |  |  |  | 0 |  |  |  | 18 | [6 empty] | 26 |  |  |  |  | 7 | [7 empty] | 5 | [9 empty] | 5
5.4 | Grow out husbandry - mullet | 23 | 43.8 | 7 |  | 3 | 2 | [13 empty] | 5.8 | [6 empty] | 10 | 12 |  |  |  |  | 4
WP6 Fish health |  |  | 247.66 | 90.1 | 84 | 23 | 0 | 37 | 0 | 4.16 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Fish health - meagre | 24 | 148.4 | 73.1 | 29 | 23 |  | 20 | [14 empty] | 3.3
6.2 | Fish health - amberjack | 25 | 95.1 | 17 | 55 |  |  | 17 |  |  | 1.1 | [6 empty] | 5
N/A | Fish health - halibut | 26 | 4.16 | [6 empty] | 4.16
WP7 Socioeconomics |  |  | 231.77 | 42 | 0 | 29.25 | 0 | 0 | 35.18 | 0 | 0 | 0 | 27 | 34 | 17.14 | 0 | 0 | 6.5 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8 | 0.1 | 0
7.1 | Institutional and organizational context | 27 | 23.65 | [5 empty] | 7 |  |  |  | 5.5 | 2.15 | 9
7.2 | New Product Development | 28 | 77.85 | 35 |  | 18.25 |  |  | 2.85 |  |  |  | 0.5 | 2.15 |  |  |  | 6.5 |  |  | 7.3 | [19 empty] | 5.3
7.3 | Consumer value perceptions and behavioral change | 29 | 75.48 | 7 |  | 8 |  |  | 12.5 |  |  |  |  | 21.88 | [6 empty] | 8.2 | [19 empty] | 17.9
7.4 | Business model and marketing strategy development | 30 | 54.79 |  |  | 3 |  |  | 12.83 |  |  |  | 21 | 7.82 | 8.14 | [5 empty] | 1 |  |  |  |  | 0.1 | 0 | 0.1 |  |  | 0.1 | 0 | [8 empty] | 0.6 | 0.1
WP8 Dissemination | Dissemination | 31 | 40.21 | 8 |  | 1 |  |  |  | 1 | 0.7 | 1 |  |  | 2.74 | 1.5 |  |  |  |  | 13.1 | [14 empty] | 2.5 | 0.42 | 3 | 2.25 | 3
Note on AA11: Constantinos Mylonas: Previously it was 76
Note on W14: Constantinos Mylonas: Previous was 6.5 PM
Note on E18: Constantinos Mylonas: From Kotzamanis 2 Aug 2013
Note on F18: Constantinos Mylonas: I reduced it from 22, to account for the reduction in budget from 75K to 45 K (proportionally). I did not get the number from Marisol
Note on X18: Constantinos Mylonas: Reduced from 0.7 to account for the reduciton in budget
Note on S19: Constantinos Mylonas: I reduced it from 5.5 to account for the reduction in budget (10K). Did not get number yet from Cova
Note on V22: Constantinos Mylonas: was 1,40
Note on V34: Constantinos Mylonas: was 3,3
Note on E36: Constantinos Mylonas: 44 Kathrios, 21.6 Chatzifotis, 3.5 Fountoulaki, 4 Kotou New numbers after addition to panterlis
Note on O42: Constantinos Mylonas: Initial value was 24,88
Note on AP42: Constantinos Mylonas: Πprevious was 13,2. Plus 3 PM from AU. Check if this is OK with HRH
Note on J43: Constantinos Mylonas: Was 11.5
Note on V44: Constantinos Mylonas: Was 10,6

## STaff effort in Proposal
DIVERSIFY
KBBE 2013.1.2.09. Diversification of fish species and products in aquaculture
Calculation of staff effort per parter and sub WP
[7 empty] | RTD partners | [6 empty] | RTD partners |  |  |  |  | RTD partners | [5 empty] | SME partners
Work Package | Description | Total | 1. HCMR | 2. FCPCT | 3. IRTA | 4. IOLR | 5. UNIABDN | 6. LEI | 7. IMR | 8. IEO | 9. UL | 10. TU/e | 11. AU | 12. APROMAR | 13. UNIBA | 14. IFREMER | 15. ULL | 16. FUNDP | 17. NIFES | 18. CTAQUA | 19. CMRM | 20. SARC | 21. DTU | 22. SWH | 23. ARGO | 24. ITICAL | 25. DAG | 26. GEI | 27. FORKYS | 28. CANEXMAR | 29. ASIALOR | 30. CULMAREX | 31. IRIDA
|  | 1544.13 | 322.05 | 288 | 85 | 70 | 38 | 32.43 | 19.5 | 34.1 | 47 | 26.5 | 35 | 20.4 | 41 | 9 | 55.6 | 39.5 | 8 | 26.6 | 14.4 | 7.5 | 20.5 | 8.5 | 65 | 29.3 | 18.5 | 12.5 | 30.5 | 75.5 | 42.5 | 18.5 | 3.25
WP1 Management |  | 82.6 | 55 | 6 | 2 | 3 | 1 | 2 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.6 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25
WP2 Reproduction and Genetics |  | 255.45 | 45 | 26 | 12 | 21 | 0 | 0 | 8 | 12.2 | 1 | 0 | 0 | 0 | 33.7 | 8.75 | 8.1 | 0 | 1 | 0 | 6.4 | 0 | 0 | 5 | 34.5 | 28.8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 2.1 meagre | 33.75 | 15 | 7 | 9 | [10 empty] | 2.75
| 2.2 amberjack | 152.1 | 17.1 | 19 |  | 14 |  |  |  | 5.6 |  |  |  |  | 30 | 2.5 | 3.8 | [7 empty] | 34.5 | 25.6
| 2.3 pike perch | 5 | 4 | [7 empty] | 1
| 2.4 halibut | 14.5 | 0.5 | [5 empty] | 8 | [9 empty] | 1 |  |  |  |  | 5
| 2.5 wreckfish | 25.8 | 7.9 |  | 1 |  |  |  |  | 6.6 | [5 empty] | 3 | 0.9 |  |  |  | 6.4
| 2.6 mullet | 24.3 | 0.5 |  | 2 | 7 | [8 empty] | 3.7 | 0.5 | 3.4 | [8 empty] | 3.2 | 4
WP3 Nutrition |  | 374.2 | 53.3 | 149 | 11 | 40 | 0 | 0 | 1 | 5.4 | 0 | 0 | 0 | 0 | 5.3 | 0 | 25.2 | 13 | 5.5 | 1.4 | 3.1 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16 | 0 | 0
| 3.1 meagre | 122.8 | 35.6 | 63 | 11 | [11 empty] | 5.4 | 2 | 1.3 |  |  | 3.5 | 1
| 3.2 amberjack | 142.7 | 17.7 | 71 |  | 6 |  |  |  | 4.5 | [6 empty] | 10.5 |  |  |  |  | 3 | [7 empty] | 30
| 3.3 pike perch | 42.6 |  | 4 | [12 empty] | 4.6 | 11 |  |  |  |  | 7 | [7 empty] | 16
| 3.4 halibut | 9.9 | [6 empty] | 1 | [7 empty] | 4.7 |  | 4.2
| 3.5 wreckfish | 5.5 |  | 1 | [5 empty] | 0.9 | [10 empty] | 3.1 | 0.5
| 3.6 mullet | 50.7 |  | 10 |  | 34 | [8 empty] | 5.3 |  |  |  |  | 1.4
WP4 larval husbandry |  | 192.85 | 33.75 | 40 | 10 | 4 | 0 | 0 | 9 | 11.9 | 25 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 1 | 0 | 4.4 | 0 | 5 | 3 | 0 | 0 | 4 | 0 | 15 | 0 | 16 | 0 | 0
| 4.1 meagre | 6.3 |  |  | 4 | [11 empty] | 2.3
| 4.2 amberjack | 89 | 20 | 40 | [5 empty] | 5.5 | [6 empty] | 8.5 | [11 empty] | 15
| 4.3 pike perch | 49 |  |  | 3 | [5 empty] | 25 | [11 empty] | 5 | [7 empty] | 16
| 4.4 halibut | 13 | [6 empty] | 9 | [9 empty] | 1 |  |  |  |  | 3
| 4.5 wreckfish | 24.55 | 13.75 | [6 empty] | 6.4 | [10 empty] | 4.4
| 4.6 mullet | 11 |  |  | 3 | 4 | [20 empty] | 4
WP5 Grow out husbandry |  | 299.9 | 66.5 | 18 | 8 | 2 | 0.2 | 0 | 0 | 3.4 | 18 | 0 | 0 | 0 | 0 | 0 | 4.5 | 26 | 0 | 3.3 | 0 | 0 | 7 | 0 | 30 | 0 | 10 | 12 | 15 | 45 | 10 | 18 | 3
| 5.1 meagre | 102.5 | 48.5 |  | 6 | [19 empty] | 30 | [6 empty] | 18
| 5.2 amberjack | 96.9 | 11 | 18 | [5 empty] | 3.4 | [6 empty] | 4.5 | [11 empty] | 15 | 45
| 5.3 pike perch | 61.2 |  |  |  |  | 0.2 |  |  |  | 18 | [6 empty] | 26 |  |  |  |  | 7 | [7 empty] | 10
| 5.4 mullet | 39.3 | 7 |  | 2 | 2 | [13 empty] | 3.3 | [6 empty] | 10 | 12 |  |  |  |  | 3
WP6 Fish health |  | 130.3 | 24.5 | 49 | 20 | 0 | 36.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 meagre | 62.9 | 14.5 | 10 | 20 |  | 18.4
| 6.2 amberjack | 67.4 | 10 | 39 |  |  | 18.4
WP7 Socioeconomics |  | 195.83 | 42 | 0 | 21 | 0 | 0 | 30.43 | 0 | 0 | 0 | 26 | 34.5 | 18.9 | 0 | 0 | 6.5 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.1 Institutional and organizational context | 26.4 | [5 empty] | 7 |  |  |  | 5.5 | 3.9 | 10
| 7.2 New Product Development | 66.05 | 35 |  | 10 |  |  | 2.85 |  |  |  | 0.5 | 3.9 |  |  |  | 6.5 |  |  | 7.3
| 7.3 Consumer value perceptions and behavioral change | 55.09 | 7 |  | 8 |  |  | 10.69 |  |  |  |  | 21.2 | [6 empty] | 8.2
| 7.4 Business model and marketing strategy development | 48.29 |  |  | 3 |  |  | 9.89 |  |  |  | 20 | 5.5 | 8.9 | [5 empty] | 1
WP8 Dissemination |  | 13 | 2 |  | 1 |  |  |  | 1 | 0.7 | 1 |  |  | 0.9 | 1.5 |  |  |  |  | 4.9

## Amend 2
DIVERSIFY | Ammend 2 (Ittical/Culmarex) | version 2 | 301/10/2015
KBBE 2013.1.2.09. Diversification of fish species and products in aquaculture |  |  |  | Amnd 2 | [21 empty] | Amnd 2 | Amnd 2
Calculation of staff effort per parter and sub WP
|  | PM from Proposal | 1546.13 | 322.05 | 288 | 85 | 70 | 38 | 32.43 | 19.5 | 34.1 | 47 | 26.5 | 35 | 20.4 | 41 | 9 | 55.6 | 39.5 | 8 | 26.6 | 14.4 | 7.5 | 20.5 | 8.5 | 65 | 29.3 | 18.5 | 12.5 | 30.5 | 75.5 | 42.5 | 18.5 | 3.25
|  | Change | 1.505% | 1.848% | -11.11% | 14.12% | 2.857% | 0% | 10.55% | 46.97% | -7.625% | -27.66% | 3.774% | 7.143% | 0.4412% | 0% | 0% | -4.856% | -12.66% | 6.25% | 21.43% | -5.556% | 26.67% | -4.878% | 105.9% | 54.77% | -28.33% | 0.5405% | 0% | 0% | -23.71% | 0.2353% | -94.05% | 30.77%
|  |  | Confirmation 2 Aug 2013 | [19 empty] | 30 Sept |  | Birgitta
[8 empty] | RTD partners | [6 empty] | RTD partners |  |  |  |  | RTD partners | [5 empty] | SME partners | [8 empty] | New Partners
Work Package (Proposal) | Title | DOW WP | Total | 1. HCMR | 2. FCPCT | 3. IRTA | 4. IOLR | 5. UNIABDN | 6.DLO | 7. IMR | 8. IEO | 9. UL | 10. TU/e | 11. AU | 12. APROMAR | 13. UNIBA | 14. IFREMER | 15. ULL | 16. FUNDP | 17. NIFES | 18. CTAQUA | 19. CMRM | 20. SARC | 21. DTU | 22. SWH | 23. ARGO | 24. ITICAL | 25. DOR | 26. GEI | 27. FORKYS | 28. CANEXMAR | 29. ASIALOR | 30. CULMAREX | 31. IRIDA | 32. MC2 | 33. FGM | 34. BVFi | 35. MASZ | 36. ANF | 37. EUFIC | 38. HRH
|  |  | 1569.4 | 328 | 256 | 97 | 72 | 38 | 35.85 | 28.66 | 31.5 | 34 | 27.5 | 37.5 | 20.49 | 41 | 9 | 52.9 | 34.5 | 8.5 | 32.3 | 13.6 | 9.5 | 19.5 | 17.5 | 100.6 | 21 | 18.6 | 12.5 | 30.5 | 57.6 | 42.6 | 1.1 | 4.25 | 3.32 | 2.75 | 0.58 | 3.25 | 3 | 3.25 | 19.7
WP1 Management | Management | 1 | 81.07 | 55 | 5 | 1.35 | 2 | 1 | 2 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.61 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1 | 0.25 | 0.25 | 0.25 | 0.16 | 0.25 | 0.75 | 0.25 | 0.6
WP2 Reproduction and Genetics |  |  | 300.51 | 46.9 | 26 | 19.9 | 21 | 0 | 0 | 8 | 12.2 | 1 | 0 | 0 | 0 | 33.7 | 8.75 | 8.1 | 0 | 1 | 0 | 6.5 | 0 | 0 | 11 | 70 | 20.4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Reproduction - meagre | 2 | 40.65 | 15 | 7 | 15.9 | [10 empty] | 2.75
2.2 | Reproduction - amberjack | 3 | 181.1 | 19 | 19 |  | 14 |  |  |  | 5.6 |  |  |  |  | 30 | 2.5 | 3.8 | [7 empty] | 70 | 17.2
2.3 | Reproduction - pikeperch | 4 | 5 | 4 | [7 empty] | 1
2.4 | Reproduction - halibut | 5 | 20.5 | 0.5 | [5 empty] | 8 | [9 empty] | 1 |  |  |  |  | 11
2.5 | Reproduction - wreckfish | 6 | 28.96 | 7.9 |  | 2 |  |  |  |  | 6.6 | [5 empty] | 3 | 0.9 |  |  |  | 6.5 | [12 empty] | 2.06
2.6 | Reproduction - mullet | 7 | 24.3 | 0.5 |  | 2 | 7 | [8 empty] | 3.7 | 0.5 | 3.4 | [8 empty] | 3.2 | 4
WP3 Nutrition |  |  | 199.9 | 6 | 65 | 1.1 | 38 | 0 | 0 | 2 | 3.9 | 0 | 0 | 0 | 0 | 5.3 | 0 | 18.5 | 8 | 6 | 1.4 | 3.5 | 5.7 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Nutrition - meagre | 8 | 27 | 0 | 20 | 0 | [11 empty] | 4.5 |  | 0 |  |  | 1.5 | 1
3.2 | Nutrition - amberjack | 9 | 46.8 | 6 | 18 | [5 empty] | 2.8 | [6 empty] | 5.5 |  |  |  |  | 2.5 | [7 empty] | 12
3.3 | Nutrition - pikeperch | 10 | 39.5 |  | 5 |  | 0 | [10 empty] | 4 | 8 |  |  |  |  | 6.5 | [7 empty] | 16
3.4 | Nutrition - halibut | 11 | 14.2 | [6 empty] | 2 | [7 empty] | 4.5 |  | 6 |  |  | 1.7
3.5 | Nutrition - wreckfish | 12 | 6.6 |  | 2 | [5 empty] | 1.1 | [10 empty] | 3.5 | 0
3.6 | Nutrition - mullet | 13 | 65.8 |  | 20 | 1.1 | 38 | [8 empty] | 5.3 |  |  |  |  | 1.4
WP4 larval husbandry |  |  | 168.51 | 17 | 40 | 6.4 | 9 | 0 | 0 | 13 | 9.7 | 13 | 0 | 0 | 0 | 0 | 0 | 9.8 | 0 | 1 | 0 | 3.1 | 0 | 4.5 | 6 | 0 | 0 | 4 | 0 | 15 | 0 | 16 | 0 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Larval husbandry - meagre | 14 | 3.7 |  |  | 2.4 | [11 empty] | 1.3
4.2 | Larval husbandry - amberjack | 15 | 79.5 | 10.5 | 40 | [5 empty] | 5.5 | [6 empty] | 8.5 | [11 empty] | 15
4.3 | Larval husbandry - pikeperch | 16 | 35.5 |  |  | 2 | [5 empty] | 13 | [11 empty] | 4.5 | [7 empty] | 16
4.4 | Larval husbandry - halibut | 17 | 20 | [6 empty] | 13 | [9 empty] | 1 |  |  |  |  | 6
4.5 | Larval husbandry - wreckfish | 18 | 14.81 | 6.5 | [6 empty] | 4.2 | [10 empty] | 3.1 | [12 empty] | 1.01
4.6 | Larval husbandry - mullet | 19 | 15 |  |  | 2 | 9 | [20 empty] | 4
WP5 Grow out husbandry |  |  | 305.2 | 63 | 36 | 15 | 2 | 0 | 0 | 0 | 3.4 | 18 | 0 | 0 | 0 | 0 | 0 | 4.5 | 26 | 0 | 3.3 | 0 | 0 | 7 | 0 | 30 | 0 | 10 | 12 | 15 | 45 | 10 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Grow out husbandry - meagre | 20 | 91.5 | 48.5 |  | 12 | [19 empty] | 30 | [6 empty] | 1
5.2 | Grow out husbandry - amberjack | 21 | 111.4 | 7.5 | 36 | [5 empty] | 3.4 | [6 empty] | 4.5 | [11 empty] | 15 | 45
5.3 | Grow out husbandry - pike perch | 22 | 61 |  |  |  |  | 0 |  |  |  | 18 | [6 empty] | 26 |  |  |  |  | 7 | [7 empty] | 10
5.4 | Grow out husbandry - mullet | 23 | 41.3 | 7 |  | 3 | 2 | [13 empty] | 3.3 | [6 empty] | 10 | 12 |  |  |  |  | 4
WP6 Fish health |  |  | 247.66 | 90.1 | 84 | 23 | 0 | 37 | 0 | 4.16 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Fish health - meagre | 24 | 148.4 | 73.1 | 29 | 23 |  | 20 | [14 empty] | 3.3
6.2 | Fish health - amberjack | 25 | 95.1 | 17 | 55 |  |  | 17 |  |  | 1.1 | [6 empty] | 5
N/A | Fish health - halibut | 26 | 4.16 | [6 empty] | 4.16
WP7 Socioeconomics |  |  | 228.84 | 42 | 0 | 29.25 | 0 | 0 | 33.85 | 0 | 0 | 0 | 27 | 37 | 17.14 | 0 | 0 | 6.5 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.1
7.1 | Institutional and organizational context | 27 | 23.65 | [5 empty] | 7 |  |  |  | 5.5 | 2.15 | 9
7.2 | New Product Development | 28 | 77.85 | 35 |  | 18.25 |  |  | 2.85 |  |  |  | 0.5 | 2.15 |  |  |  | 6.5 |  |  | 7.3 | [19 empty] | 5.3
7.3 | Consumer value perceptions and behavioral change | 29 | 73.78 | 7 |  | 8 |  |  | 12.5 |  |  |  |  | 24.88 | [6 empty] | 8.2 | [19 empty] | 13.2
7.4 | Business model and marketing strategy development | 30 | 53.56 |  |  | 3 |  |  | 11.5 |  |  |  | 21 | 7.82 | 8.14 | [5 empty] | 1 |  |  |  |  | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | [8 empty] | 0.6
WP8 Dissemination | Dissemination | 31 | 37.71 | 8 |  | 1 |  |  |  | 1 | 0.7 | 1 |  |  | 2.74 | 1.5 |  |  |  |  | 10.6 | [14 empty] | 2.5 | 0.42 | 3 | 2.25 | 3
Note on E21: Constantinos Mylonas: From Kotzamanis 2 Aug 2013
Note on F21: Constantinos Mylonas: I reduced it from 22, to account for the reduction in budget from 75K to 45 K (proportionally). I did not get the number from Marisol
Note on X21: Constantinos Mylonas: Reduced from 0.7 to account for the reduciton in budget
Note on S22: Constantinos Mylonas: I reduced it from 5.5 to account for the reduction in budget (10K). Did not get number yet from Cova
Note on E39: Constantinos Mylonas: 44 Kathrios, 21.6 Chatzifotis, 3.5 Fountoulaki, 4 Kotou New numbers after addition to panterlis